## bus_ticketing_system_20161225_1
Id | Title | Labels | Iteration | Iteration Start | Iteration End | Type | Estimate | Current State | Created at | Accepted at | Deadline | Requested By | Description | URL | Other ID | Integration | Owned By | Owned By | Task | Task Status | Task | Task Status | Task | Task Status | Task | Task Status | Task | Task Status
3158053 | Bus Schedule | busschedule |  |  |  | epic |  |  | Nov 15, 2016 |  |  |  | To enable staff to add the Bus schedule | https://www.pivotaltracker.com/epic/show/3158053
3158031 | Payment | payment |  |  |  | epic |  |  | Nov 15, 2016 |  |  |  | This module enable customer to make ticket payment | https://www.pivotaltracker.com/epic/show/3158031
3158019 | Login | login |  |  |  | epic |  |  | Nov 15, 2016 |  |  |  | This module enable customer to login to their profile. | https://www.pivotaltracker.com/epic/show/3158019
3157971 | Booking | booking |  |  |  | epic |  |  | Nov 15, 2016 |  |  |  | This module enable customer to book ticket | https://www.pivotaltracker.com/epic/show/3157971
134637089 | Edit profile | login | 1 | Nov 15, 2016 | Nov 27, 2016 | feature | 1 | accepted | Nov 15, 2016 | Nov 27, 2016 |  | Jack Fire | As a customer , I should able to edit the profile so that I can update my information when there is any changes. | https://www.pivotaltracker.com/story/show/134637089 |  |  | JIE HAN CHONG |  | Retrieve customer information from the database. | completed | Update the customer information in the database. | completed | Edit the customer information. | completed
134636471 | Book Ticket | booking | 1 | Nov 15, 2016 | Nov 27, 2016 | feature | 3 | accepted | Nov 15, 2016 | Nov 27, 2016 |  | alvin khor | As a customer, I should be able to book a bus ticket in order to travel to other places | https://www.pivotaltracker.com/story/show/134636471 |  |  | alvin khor | JIE HAN CHONG | Display list of available travel location | completed | Choose booking details | completed | Retrieve bus seat availability from database | completed | Book bus seat(s) | completed | Update booking information into the database | completed
134636761 | View Ticket | booking | 1 | Nov 15, 2016 | Nov 27, 2016 | feature | 1 | accepted | Nov 15, 2016 | Nov 27, 2016 |  | JIE HAN CHONG | As a customer, I should be able to view my current booking information so that I am able to download and use it as a boarding pass. | https://www.pivotaltracker.com/story/show/134636761 |  |  | JIE HAN CHONG |  | Retrieve customer specified booking information from the database. | completed | Display the booking information to the customer. | completed
134636609 | Update Ticket | booking | 1 | Nov 15, 2016 | Nov 27, 2016 | feature | 2 | accepted | Nov 15, 2016 | Nov 27, 2016 |  | alvin khor | As a customer, I should be able to change my ticket details a week before the date of departure. This can provide convenience to me as I can choose a more suitable date and time. | https://www.pivotaltracker.com/story/show/134636609 |  |  | alvin khor | JIE HAN CHONG | Retrieve booked ticket information from the database | completed | Reselect booking details | completed | Check availability of the reselected booking information | completed | Update booking details into the database | completed
134636907 | Delete Ticket | booking | 1 | Nov 15, 2016 | Nov 27, 2016 | feature | 2 | accepted | Nov 15, 2016 | Nov 27, 2016 |  | JIE HAN CHONG | As a customer, I should be able to cancel my ticket within a week time before the departure date and get a refund so that I would not be wasting my money. | https://www.pivotaltracker.com/story/show/134636907 |  |  | JIE HAN CHONG |  | Retrieve customer booked ticket information from the database. | completed | Choose a booked ticket to be cancelled. | completed | Check the duration between current date and date of departure. | completed | Update the seat availability in the database. | completed | Delete the booking information from the database. | completed
134637159 | Login to Main Menu | login | 1 | Nov 15, 2016 | Nov 27, 2016 | feature | 1 | accepted | Nov 15, 2016 | Nov 27, 2016 |  | Jack Fire | As a customer, I should able to login to the system in order to be eligible for promotion and get updated about the bus schedule. | https://www.pivotaltracker.com/story/show/134637159 |  |  | JIE HAN CHONG |  | Get username and password. | completed | Verify username and password from the database. | completed | Display main menu. | completed
134637959 | Make Payment | payment | 2 | Nov 28, 2016 | Dec 11, 2016 | feature | 3 | started | Nov 15, 2016 |  |  | Kenn Chew | As a customer, I should be able to make ticket payment in order to purchase the ticket | https://www.pivotaltracker.com/story/show/134637959 |  |  | Jack Fire |  | Display the payment summary of the ticket. | not completed | Select the payment method and fill in the payment details | not completed | Check and confirm the payment details | not completed | Pay the ticket transaction | not completed | Update payment information into the database | not completed
134637967 | View Payment History | payment | 2 | Nov 28, 2016 | Dec 11, 2016 | feature | 3 | started | Nov 15, 2016 |  |  | Kenn Chew | As a customer, I should be able to view my payment history so that I am able to refer and check back my every transactions. | https://www.pivotaltracker.com/story/show/134637967 |  |  | Chun Hui |  | Select the date of the payment transaction | not completed | Retrieve customer specified date payment information from the database | not completed | Display the payment information to the customer | not completed
134638013 | Cancel Payment | payment | 2 | Nov 28, 2016 | Dec 11, 2016 | feature | 3 | started | Nov 15, 2016 |  |  | Kenn Chew | As a customer, I should be able to cancel my ticket payment within a week time before the departure date and get a refund if I wish to cancel the travel. | https://www.pivotaltracker.com/story/show/134638013 |  |  | Kenn Chew |  | Retrieve customer payment ticket information from the database. | not completed | Choose a paid ticket to be cancelled | not completed | Cancel the payment information from the database | not completed | Update the seat availability and payment information in the database | not completed
134638267 | View Bus Schedule | busschedule | 3 | Dec 12, 2016 | Dec 25, 2016 | feature | 3 | unstarted | Nov 15, 2016 |  |  | Chun Hui | As a staff, I should able to view the ongoing bus schedule so that I can know the number of passenger for that specific bus trip. | https://www.pivotaltracker.com/story/show/134638267 |  |  | alvin khor |  | Display all bus schedule from the database | not completed | Select the specific bus schedule from the database. | not completed | Display the selected bus schedule information. | not completed
134638319 | Update Bus Schdule | busschedule | 3 | Dec 12, 2016 | Dec 25, 2016 | feature | 3 | unstarted | Nov 15, 2016 |  |  | Chun Hui | As a staff , I should able to edit the bus schedule information if there's any changes to the schedule. This is to make sure the information of bus schedule is always correct. | https://www.pivotaltracker.com/story/show/134638319 |  |  | Chun Hui |  | Retrieve the bus schedule from the database | not completed | Select which bus schedule want to update from the database | not completed | Edit the details of the bus schedule | not completed | Update the bus schedule into the database | not completed
134638369 | Add Bus Schedule | busschedule | 3 | Dec 12, 2016 | Dec 25, 2016 | feature | 3 | unstarted | Nov 15, 2016 |  |  | Chun Hui | As a staff, I should be able to add a new bus schedule so that the tickets can be sell to customers who want to travel to other places. | https://www.pivotaltracker.com/story/show/134638369 |  |  | JIE HAN CHONG |  | Display the add bus schedule form | not completed | Fill in all the bus schedule information | not completed | Updatethe bus schedule information into the database | not completed